## Dashboard
FASTag Redesign India - PM Control Tower
Generated 19 Jun 2026 ¦ North Star: Successful toll crossings without user intervention
KPI | Target | Module | Status | Owner | Risk | Next Action
Pilot duration | 90 days | Toll Health | Now | Product + Issuer | Medium | Lock status signals
Issue diagnosis coverage | >=80% | Transaction Ledger | Now | Product + Operator | High | Define event schema
Dispute creation time | <60 sec | Dispute Tracker | Now | Product + NPCI/Issuer | High | Map reason codes
User comprehension | >=70% | Annual Pass Card | Now | Product | Medium | Eligibility/rules engine
Fleet at-risk detection | >=90% | Fleet Control Tower | Next | SMB/Fleet PM | Medium | Pilot with 3 fleets
|  | Operator Queue | Next | Ops PM | High | Shadow-mode anomaly test
|  | ANPR/GNSS Bridge | Later | Platform | High | Policy and privacy design
|  | WhatsApp Alerts | Next | Growth/Support | Low | Design alert taxonomy

## Roadmap
Horizon | Outcome | Epic | Scope | Primary metric | Confidence | Dependencies
Now | Users can confirm toll readiness and understand charges | FASTag Health | Vehicle profile, balance, KYC, issuer, duplicate tag, blocked risk | Issue diagnosis coverage | High | Issuer/NHAI status feed
Now | Users can explain and dispute recent deductions | Transaction Timeline | Plaza, timestamp, amount, pass/wallet source, evidence summary | User comprehension | High | Toll event schema
Now | Users can raise common complaints quickly | Dispute Tracker | Wrong/double/no-travel/wrong-class/pass-not-applied dispute flow | Dispute creation time | Medium | Reason codes and SLAs
Now | Annual pass users understand benefits | Annual Pass Card | Trips left, validity, eligible tolls, pass applied indicator | Pass clarity score | High | Rajmarg rules feed
Next | Fleet owners prevent vehicle stoppage | Fleet Control Tower | Multi-vehicle health, bulk recharge, alerts, toll spend | At-risk vehicles resolved before travel | Medium | Fleet pilot users
Next | Operators reduce exception noise | Operator Exception Queue | Duplicate read, failed read, class mismatch, ANPR mismatch | Manual triage load | Medium | Operator event data
Next | Users receive actionable alerts | WhatsApp/SMS Alerts | Low balance, KYC, pass expiry, dispute update | Alert action rate | Medium | Messaging provider
Later | System prepares for hybrid tolling | ANPR + GNSS Bridge | Consent, privacy, distance billing explanation, image audit | Hybrid toll event accuracy | Low | Policy decision and infrastructure

## Backlog
ID | Epic | Story | Segment | R | I | C | E | RICE | Priority | Status | Not Now Reason
B-001 | Toll Health | Show active/warning/blocked state with root cause | Citizen | 10 | 3 | 0.85 | 3 | 8.5 | P0 | Ready
B-002 | Toll Health | Explain KYC, low balance, issuer unavailable, duplicate tag | Citizen | 9 | 3 | 0.75 | 4 | 5.0625 | P0 | Ready
B-003 | Transaction Ledger | Show plaza, timestamp, amount, pass/wallet source | Citizen | 10 | 3 | 0.8 | 4 | 6 | P0 | Ready
B-004 | Dispute Tracker | Raise wrong/double deduction dispute with evidence | Citizen | 8 | 3 | 0.65 | 5 | 3.12 | P0 | Shape
B-005 | Annual Pass | Show trips left, validity, eligible tolls | Citizen | 7 | 2 | 0.8 | 2 | 5.6 | P0 | Ready
B-006 | Route Planner | Estimate route toll and recharge need | Traveller | 6 | 2 | 0.7 | 4 | 2.1 | P1 | Shape
B-007 | Fleet Control | Bulk low-balance and blocked alerts | Fleet | 6 | 3 | 0.7 | 4 | 3.15 | P1 | Shape
B-008 | Fleet Control | Toll spend analytics by vehicle and corridor | Fleet | 5 | 2 | 0.75 | 3 | 2.5 | P1 | Shape
B-009 | Operator Queue | Flag duplicate reads and class mismatch | Operator | 5 | 3 | 0.55 | 5 | 1.65 | P1 | Experiment
B-010 | AI Copilot | Draft dispute explanation and evidence summary | Citizen | 6 | 2 | 0.65 | 3 | 2.6 | P1 | Experiment
B-011 | GNSS Bridge | Distance-based billing explainability | Policy/Platform | 3 | 3 | 0.25 | 8 | 0.28125 | P3 | Not Now | Too policy-dependent for MVP
B-012 | Loyalty | Rewards for frequent toll users | Citizen | 4 | 1 | 0.4 | 4 | 0.4 | P3 | Not Now | Does not solve trust or reliability

## Metrics
Metric Type | Metric | Definition | Target / Guardrail | Event(s) to instrument
North Star | Successful toll crossings without user intervention | Crossing succeeds, correct amount/pass is applied, no manual complaint needed | Increase over baseline | toll_crossing_completed, complaint_created
Input | FASTag active health rate | % vehicles showing Active before travel | >=95% for pilot users | health_status_viewed, status_resolved
Input | First-pass read success rate | % crossings with successful first read | Improve vs pilot baseline | toll_read_success, toll_read_failed
Input | Wrong deduction rate | Disputed deductions per 1,000 crossings | Reduce vs baseline | dispute_created, dispute_reason_selected
Input | Dispute resolution TAT | Median time from ticket creation to outcome | Reduce by 30% | dispute_created, dispute_status_updated
Input | Auto top-up success rate | % top-up attempts successful | >=98% | topup_started, topup_success, topup_failed
Input | Annual pass clarity score | % users who understand pass use/validity in tests | >=70% | pass_card_viewed, pass_rules_opened
Guardrail | False blacklist rate | Wrongly blocked vehicles / blocked vehicles | Must not increase | blacklist_state_changed
Guardrail | Fraud leakage | Estimated revenue leakage due to misuse | Must not increase | fraud_flag_created
Guardrail | Manual intervention load | Tickets requiring manual support per 1,000 users | Reduce | support_ticket_created
Guardrail | Privacy incidents | Confirmed privacy/compliance incidents | 0 | privacy_incident_created

## Risks
Risk | Type | Impact | Confidence | Risk Score | Cheapest Test | Kill Criterion | Owner
Limited issuer/toll data access | Feasibility | 5 | 2 | 20 | Pilot with one issuer and one corridor | Cannot explain >80% of warning states | Partnerships
Status accuracy differs from plaza reality | Value/Trust | 5 | 2 | 20 | Shadow-mode compare status vs actual outcomes | False confidence causes user harm | Product
Dispute workflow remains opaque | Viability | 4 | 3 | 12 | Map reason codes and SLA events | No visible owner/stage for disputes | Ops
Annual pass rules misunderstood | Usability | 3 | 3 | 9 | Run pass card usability test | <70% understand validity/trips | Design
AI over-automates sensitive decisions | Trust/Compliance | 5 | 4 | 10 | Keep AI suggest-only in pilot | Any AI-only penalty/blacklist/refund rejection | Governance
Fleet admins ignore dashboard | Value | 4 | 2 | 16 | Pilot with 10 fleets and observe use | <3 paid-pilot follow-ups | GTM

## Experiments
Hypothesis | Test Type | Sample | Decision Metric | Go Rule | Owner | Status
Users will check toll health before trips | Clickable prototype | 20 vehicle owners | Task completion + intent | >=60% would use and understand fix | Product/Design | Planned
Dispute tracker reduces anxiety | Prototype usability | 15 users with past disputes | Creation time + preference | <60 sec and >=50% prefer | Product | Planned
Fleet admins will pay for control tower | Demo + LOI | 10 fleet owners | Paid pilot interest | >=3 strong follow-ups | GTM | Planned
Operator queue reduces manual work | Shadow-mode data test | Sample toll events | Useful anomaly precision | Useful precision in operator review | Ops/ML | Planned
Annual pass optimizer is understood | Usability test | 20 private vehicle owners | Comprehension score | >=70% understand pass vs wallet | Design | Planned

## Source_Log
Source | URL | Used for
IHMCL ETC Transaction Reports | https://ihmcl.co.in/etc-transaction-reports/ | FASTag scale and transaction/collection context
IHMCL FASTag User Information | https://ihmcl.co.in/fastag-user/ | FASTag user/technology context
NHAI One Vehicle One FASTag press release | https://nhai.gov.in/nhai/sites/default/files/2024-01/Press_Release-One_Vehical_One_FASTag_0.pdf | KYC, duplicate tag and blacklisting context
PIB clarification on satellite tolling | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2122632 | Policy guardrail for FASTag vs GNSS transition
Rajmarg Yatra Annual Pass | https://rajmargyatra.nhai.gov.in/annual-pass | Annual pass UX and pricing context
Rajmarg Yatra Annual Pass Terms | https://rajmargyatra.nhai.gov.in/annual-pass/terms-and-conditions | Validity, crossings, pricing, refund rules
NPCI NETC Circulars | https://www.npci.org.in/circulars/netc | NETC dispute and chargeback context
NPCI NETC FASTag Status | https://www.npci.org.in/netcfastag-status | Status check context