## Dashboard
Portfolio Audit — saikiranbiswal.github.io/portfolio
Prepared 2026-06-24 · Goal: make a PM / hiring manager / VP of Product hit an 'aha' moment
Total open issues | P0 — Critical | P1 — Important | P2 — Polish
23 | 6 | 10 | 7
By Severity |  |  | By Category
Severity | Count |  | Category | Count
P0 | 6 |  | Content & Consistency | 8
P1 | 10 |  | Navigation & IA | 4
P2 | 7 |  | Technical & Hygiene | 4
|  |  | SEO & Accessibility | 3
|  |  | Visual & Brand | 3
|  |  | Mobile & Responsive | 1
Top priorities (start here)
ID | Issue |  |  | Sev
P-03 | Inconsistent headline stats across pages (8 vs 9 products, 2 vs 3 case studies) |  |  | P0
P-01 | Mobile nav overflows — 'Contact' is cut off, no hamburger menu |  |  | P0
P-04 | Job title is inconsistent across the site & résumé |  |  | P0
P-05 | No og:image / Twitter card on any page — links show no preview when shared |  |  | P0
P-06 | Mobile homepage gallery is unreadable — cards overlap, hero crowded |  |  | P0
P-02 | Homepage value prop & headline live inside <canvas> — invisible to SEO & screen readers |  |  | P0

## Master Issue Log
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-01 | Mobile nav overflows — 'Contact' is cut off, no hamburger menu | Navigation & IA | All pages (global header) @ ≤420px | Bug | P0 | 5 | 2 | 5 | Add a responsive breakpoint: collapse nav into a hamburger/drawer under ~640px; ensure all six items + status remain reachable. | Open | Sai
P-02 | Homepage value prop & headline live inside <canvas> — invisible to SEO & screen readers | SEO & Accessibility | index.html (hero gallery) | Bug | P0 | 5 | 4 | 2.5 | Render the headline and a text fallback list of projects as real HTML behind/below the canvas (progressive enhancement). Keep canvas as a visual layer only. | Open | Sai
P-03 | Inconsistent headline stats across pages (8 vs 9 products, 2 vs 3 case studies) | Content & Consistency | products.html vs labs.html | Content | P0 | 4 | 1 | 8 | Decide the canonical numbers and propagate from a single source (content/site.json). A VP will notice mismatched self-reported metrics. | Open | Sai
P-04 | Job title is inconsistent across the site & résumé | Content & Consistency | Global / case studies / résumé | Content | P0 | 4 | 2 | 4 | Choose ONE primary title and apply everywhere incl. the résumé PDF and case-study Role fields. | Open | Sai
P-05 | No og:image / Twitter card on any page — links show no preview when shared | SEO & Accessibility | All top-level pages | SEO | P0 | 4 | 2 | 4 | Add og:image (1200×630), og:url, twitter:card=summary_large_image to every page. Generate a branded share card. | Open | Sai
P-06 | Mobile homepage gallery is unreadable — cards overlap, hero crowded | Mobile & Responsive | index.html @ 375px | UX | P0 | 4 | 3 | 2.7 | Provide a mobile-specific layout: replace the free-floating canvas with a clean stacked list of projects under the headline. | Open | Sai
P-07 | IA redundancy: 'Work', 'Labs', and 'Artifacts' overlap and confuse the taxonomy | Navigation & IA | Global nav | UX | P1 | 4 | 3 | 2.7 | Collapse to a clearer model, e.g. Work (case studies) / Playground (interactive apps) / Artifacts (downloads), with no content shown in two places. | Open | Sai
P-08 | Canvas project cards are not real links / not keyboard-navigable | SEO & Accessibility | index.html hero | Bug | P1 | 3 | 3 | 2 | Mirror each project as a focusable, labelled link in the DOM fallback added in P-02. | Open | Sai
P-09 | Case-study status ambiguity — FASTag is a 3rd case study but demoted to 'Selected Work' | Content & Consistency | products.html | Content | P1 | 3 | 2 | 3 | Either promote FASTag to flagship or relabel the stat; make case-study tiering explicit and consistent. | Open | Sai
P-10 | labs.html metadata contradicts itself (five vs six labs) | Content & Consistency | labs.html <head> + body | Content | P1 | 2 | 1 | 4 | Pick the correct lab count and align title, og:title, and the visible stat. | Open | Sai
P-11 | Brand accent color inconsistent — case studies use blue, main site uses coral | Visual & Brand | case-studies/*.html vs main site | UX | P1 | 3 | 2 | 3 | Unify the accent token and header treatment across case-study pages and the main shell. | Open | Sai
P-12 | Duplicate / orphaned artifact directories bloat the repo | Technical & Hygiene | artifacts/ vs assets/artifacts/files/ | Tech | P1 | 2 | 2 | 2 | Confirm the canonical location, delete the orphaned tree, keep one source of truth. | Open | Sai
P-13 | CMS server files committed / present in deploy surface | Technical & Hygiene | cms_server.py, .cms_server.log, admin.html | Tech | P1 | 3 | 2 | 3 | Re-add .cms_server.log to .gitignore, exclude cms_server.py from the deployed artifact, and confirm admin.html is not linked anywhere. | Open | Sai
P-14 | Public product claims not reconciled to actual stage / evidence | Content & Consistency | products.html / case studies | Content | P1 | 3 | 3 | 2 | Add an explicit, consistent stage label (Concept / Prototype / In testing / Live) to every product and case study. | Open | Sai
P-15 | Artifacts page wastes ~340px of empty space above the hero (desktop) | Visual & Brand | artifacts.html | UX | P1 | 2 | 2 | 2 | Tighten the hero top spacing / vertical rhythm so the headline sits in the upper third. | Open | Sai
P-16 | No clear primary CTA / next step for a hiring manager on the homepage | Navigation & IA | index.html | UX | P1 | 4 | 3 | 2.7 | Add a prominent primary CTA (e.g. 'See the work' → case studies) alongside the interactive gallery. | Open | Sai
P-17 | Nav label 'Work' points to products.html (label/URL mismatch) | Navigation & IA | Global nav | Tech | P2 | 1 | 1 | 2 | Rename the file to work.html (with a redirect) or accept and document; low priority. | Open | Sai
P-18 | Legacy / orphaned pages still present (gallery.html, project.html) | Technical & Hygiene | gallery.html, project.html | Tech | P2 | 2 | 2 | 2 | Remove if retired, or wire them in intentionally; add noindex if kept as scratch. | Open | Sai
P-19 | Homepage cards bleed off-screen with unreadable micro-text; one card is a recursive screenshot of the portfolio | Visual & Brand | index.html hero | UX | P2 | 2 | 2 | 2 | Curate the card set: drop the recursive card, ensure each visible card is legible or clearly decorative. | Open | Sai
P-20 | Résumé PDF title says 'Product Consultant' — align with chosen site title | Content & Consistency | assets/resume.pdf | Content | P2 | 2 | 1 | 4 | Regenerate the résumé with the single chosen title and consistent headline. | Open | Sai
P-21 | Atlas 'source gap' — confirm Atlas is a real prototype, not a placeholder | Technical & Hygiene | apps/atlas/ | Tech | P2 | 2 | 2 | 2 | Publish a real preview/state and a clear 'prototype' label, or remove from the featured list. | Open | Sai
P-22 | Verify outbound LinkedIn URL resolves | Content & Consistency | contact.html | Content | P2 | 2 | 1 | 4 | Manually verify the LinkedIn handle resolves; fix if the slug differs. | Open | Sai
P-23 | 'Open to lead PM roles' status must match the chosen title | Content & Consistency | Global header status pill | Content | P2 | 1 | 1 | 2 | Align wording once the canonical title is set. | Open | Sai

## Nav & IA
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-01 | Mobile nav overflows — 'Contact' is cut off, no hamburger menu | Navigation & IA | All pages (global header) @ ≤420px | Bug | P0 | 5 | 2 | 5 | Add a responsive breakpoint: collapse nav into a hamburger/drawer under ~640px; ensure all six items + status remain reachable. | Open | Sai
P-07 | IA redundancy: 'Work', 'Labs', and 'Artifacts' overlap and confuse the taxonomy | Navigation & IA | Global nav | UX | P1 | 4 | 3 | 2.7 | Collapse to a clearer model, e.g. Work (case studies) / Playground (interactive apps) / Artifacts (downloads), with no content shown in two places. | Open | Sai
P-16 | No clear primary CTA / next step for a hiring manager on the homepage | Navigation & IA | index.html | UX | P1 | 4 | 3 | 2.7 | Add a prominent primary CTA (e.g. 'See the work' → case studies) alongside the interactive gallery. | Open | Sai
P-17 | Nav label 'Work' points to products.html (label/URL mismatch) | Navigation & IA | Global nav | Tech | P2 | 1 | 1 | 2 | Rename the file to work.html (with a redirect) or accept and document; low priority. | Open | Sai

## SEO & A11y
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-02 | Homepage value prop & headline live inside <canvas> — invisible to SEO & screen readers | SEO & Accessibility | index.html (hero gallery) | Bug | P0 | 5 | 4 | 2.5 | Render the headline and a text fallback list of projects as real HTML behind/below the canvas (progressive enhancement). Keep canvas as a visual layer only. | Open | Sai
P-05 | No og:image / Twitter card on any page — links show no preview when shared | SEO & Accessibility | All top-level pages | SEO | P0 | 4 | 2 | 4 | Add og:image (1200×630), og:url, twitter:card=summary_large_image to every page. Generate a branded share card. | Open | Sai
P-08 | Canvas project cards are not real links / not keyboard-navigable | SEO & Accessibility | index.html hero | Bug | P1 | 3 | 3 | 2 | Mirror each project as a focusable, labelled link in the DOM fallback added in P-02. | Open | Sai

## Content
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-03 | Inconsistent headline stats across pages (8 vs 9 products, 2 vs 3 case studies) | Content & Consistency | products.html vs labs.html | Content | P0 | 4 | 1 | 8 | Decide the canonical numbers and propagate from a single source (content/site.json). A VP will notice mismatched self-reported metrics. | Open | Sai
P-04 | Job title is inconsistent across the site & résumé | Content & Consistency | Global / case studies / résumé | Content | P0 | 4 | 2 | 4 | Choose ONE primary title and apply everywhere incl. the résumé PDF and case-study Role fields. | Open | Sai
P-09 | Case-study status ambiguity — FASTag is a 3rd case study but demoted to 'Selected Work' | Content & Consistency | products.html | Content | P1 | 3 | 2 | 3 | Either promote FASTag to flagship or relabel the stat; make case-study tiering explicit and consistent. | Open | Sai
P-10 | labs.html metadata contradicts itself (five vs six labs) | Content & Consistency | labs.html <head> + body | Content | P1 | 2 | 1 | 4 | Pick the correct lab count and align title, og:title, and the visible stat. | Open | Sai
P-14 | Public product claims not reconciled to actual stage / evidence | Content & Consistency | products.html / case studies | Content | P1 | 3 | 3 | 2 | Add an explicit, consistent stage label (Concept / Prototype / In testing / Live) to every product and case study. | Open | Sai
P-20 | Résumé PDF title says 'Product Consultant' — align with chosen site title | Content & Consistency | assets/resume.pdf | Content | P2 | 2 | 1 | 4 | Regenerate the résumé with the single chosen title and consistent headline. | Open | Sai
P-22 | Verify outbound LinkedIn URL resolves | Content & Consistency | contact.html | Content | P2 | 2 | 1 | 4 | Manually verify the LinkedIn handle resolves; fix if the slug differs. | Open | Sai
P-23 | 'Open to lead PM roles' status must match the chosen title | Content & Consistency | Global header status pill | Content | P2 | 1 | 1 | 2 | Align wording once the canonical title is set. | Open | Sai

## Mobile
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-06 | Mobile homepage gallery is unreadable — cards overlap, hero crowded | Mobile & Responsive | index.html @ 375px | UX | P0 | 4 | 3 | 2.7 | Provide a mobile-specific layout: replace the free-floating canvas with a clean stacked list of projects under the headline. | Open | Sai

## Visual & Brand
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-11 | Brand accent color inconsistent — case studies use blue, main site uses coral | Visual & Brand | case-studies/*.html vs main site | UX | P1 | 3 | 2 | 3 | Unify the accent token and header treatment across case-study pages and the main shell. | Open | Sai
P-15 | Artifacts page wastes ~340px of empty space above the hero (desktop) | Visual & Brand | artifacts.html | UX | P1 | 2 | 2 | 2 | Tighten the hero top spacing / vertical rhythm so the headline sits in the upper third. | Open | Sai
P-19 | Homepage cards bleed off-screen with unreadable micro-text; one card is a recursive screenshot of the portfolio | Visual & Brand | index.html hero | UX | P2 | 2 | 2 | 2 | Curate the card set: drop the recursive card, ensure each visible card is legible or clearly decorative. | Open | Sai

## Tech & Hygiene
ID | Title | Category | Page / Location | Type | Severity | Impact | Effort | Priority Score | Evidence (what was observed) | Recommended Fix | Status | Owner
P-12 | Duplicate / orphaned artifact directories bloat the repo | Technical & Hygiene | artifacts/ vs assets/artifacts/files/ | Tech | P1 | 2 | 2 | 2 | Confirm the canonical location, delete the orphaned tree, keep one source of truth. | Open | Sai
P-13 | CMS server files committed / present in deploy surface | Technical & Hygiene | cms_server.py, .cms_server.log, admin.html | Tech | P1 | 3 | 2 | 3 | Re-add .cms_server.log to .gitignore, exclude cms_server.py from the deployed artifact, and confirm admin.html is not linked anywhere. | Open | Sai
P-18 | Legacy / orphaned pages still present (gallery.html, project.html) | Technical & Hygiene | gallery.html, project.html | Tech | P2 | 2 | 2 | 2 | Remove if retired, or wire them in intentionally; add noindex if kept as scratch. | Open | Sai
P-21 | Atlas 'source gap' — confirm Atlas is a real prototype, not a placeholder | Technical & Hygiene | apps/atlas/ | Tech | P2 | 2 | 2 | 2 | Publish a real preview/state and a clear 'prototype' label, or remove from the featured list. | Open | Sai

## Methodology
How this audit was produced
The live site was rendered in a browser preview and every top-level page, the case-study
template, and the Atlas app were inspected on desktop (1280px) and mobile (375px). The
source tree was checked for broken links, orphaned files, SEO/meta tags, and file integrity.
Severity key
P0 — Critical: breaks credibility or reachability; fix before sharing the link with a VP.
P1 — Important: noticeably weakens the story or hygiene; fix this cycle.
P2 — Polish: refinement; fix when time allows.
Priority Score = Impact / Effort × 2 (higher = do first). Impact & Effort scored 1–5 (1 = small effort).
Note on overlaps
P-04 (title), P-20 (résumé title) and P-23 (status pill) are one decision — pick a single title once.
P-02 (canvas SEO) and P-08 (canvas a11y) share the same fix (a DOM fallback).
Several items (P-14 reconcile claims, P-21 Atlas gap) were already self-identified on the Atlas board.